## Overview
KAVACH-AI — Sovereign On-Premise Agentic AI Workbench
SIH 2026 — Problem Statement 26117 ¦ Theme: Smart Automation ¦ 5-Day Build Plan
Problem Statement | SIH PS 26117 asks for a sovereign, on-premise agentic AI workbench using open-weight multimodal LLMs for confidential industrial work — secure knowledge retrieval, engineering grounding, and real operational artifacts, with zero dependency on external cloud AI.
Our Core Story (one line) | An engineer gives KAVACH-AI a real industrial task. The workbench understands it locally, picks the right local model, retrieves grounded evidence, does the work, verifies the result, generates a real document, and PROVES no data ever left the organization.
The Trap We Are Avoiding | "Connect Ollama + RAG + spit out a DOCX" is a weekend project — any team can build it. That is PLUMBING, not the product. Judges have seen this exact demo a hundred times.
THE 5 DIFFERENTIATORS — what actually wins this
1. Prove sovereignty, don't claim it | Live sovereignty panel (local services ✓ / external calls 0 / outbound traffic 0MB / sandbox network OFF). We deliberately try an internet call in front of the judge and show it blocked, live. Built Day 5.
2. Explainable router, not a hidden if-else | A visible Route Card: task type -> model selected -> WHY (capability match) -> models rejected -> confidence. Turns routing into a feature judges can inspect. Built Day 2.
3. Evidence-first, every claim traceable | Every fact in the generated report links to a document + page + revision. Stale-SOP pair (Rev-2 vs Rev-4) is used to prove the system flags conflicts and asks a human instead of silently using an old doc. Built Day 3.
4. Bounded agent, controlled agency | INTAKE -> PLAN -> RETRIEVE -> ACT -> OBSERVE -> VERIFY -> COMPLETE with max_steps=8, max_retries=2. Agent stops itself instead of looping forever — shown live as a Mission Card. Built Day 2.
5. Real deliverable + human approval gate | Not a chat reply — an actual .docx that opens cleanly, labelled "AI-generated draft — human approval required", with Approve / Modify / Reject buttons. The system never self-approves. Built Day 4.
TEAM ROSTER — 6 members, 3 machines
Name | Role | Primarily Owns
Ananya | Frontend / UI-UX Dev React portal, route card, evidence panel, sovereignty panel, final split-screen demo layout. Works on any client machine.
Aniket | Frontend / UI-UX Dev Upload/task UI, agent trace & mission card, approval buttons, audit tab. Works on any client machine.
Piyush | Backend/AI — "The Brain" (Laptop 1, RTX 4050 6GB) Ollama host for Llama-3.1-8B-Instruct (general reasoning + routing). Owns model registry + rule-based router.
Vaibhav | Backend/AI — "The Engine" (Laptop 2, RTX 4050 6GB) Ollama host for Qwen2.5-Coder-7B + Qwen2.5-VL-7B, hot-swapped by task. Owns vision/OCR/P&ID path.
Meet | Backend — "The Orchestrator" (MacBook, client/API laptop) FastAPI, job state machine, RAG/vector DB, CSV tool, DOCX generation, audit log.
Vinit | Backend — "The Orchestrator" (MacBook, client/API laptop) Endpoints, Docker sandbox, security/firewall, psutil sovereignty monitor, hashing, demo data.
MACHINE TOPOLOGY
Laptop 1 — "The Brain" (Piyush) | RTX 4050 6GB. Ollama + Llama-3.1-8B-Instruct 4-bit GGUF (~5.5GB). General reasoning + routing ONLY — do not also load a vision model here.
Laptop 2 — "The Engine" (Vaibhav) | RTX 4050 6GB. Ollama + Qwen2.5-Coder-7B (4-bit) and Qwen2.5-VL-7B (4-bit), hot-swapped by task. Verify VL-7B on real P&ID image Day 1 — if it OOMs, fall back to a 2B-class VLM.
MacBook — "The Orchestrator" (Meet + Vinit, client laptop) | Next.js/React frontend, FastAPI backend, vector DB (FAISS/Qdrant), Docker sandbox, security/audit layer. No heavy inference here.
Network | All 3 machines on one local offline switch (preferred) or a hotspot with mobile data OFF. A physical switch can be dramatically unplugged mid-demo for the sovereignty proof — a phone hotspot toggle is a weaker visual.
PRIORITY LEGEND
Critical | Blocks the demo — must complete before moving to the next day
High | Important for the day's goal — prioritise in daily stand-up
Medium | Complete within the day if time allows
Low | Nice-to-have / cut first under time pressure

## Day 1
DAY 1 — Infrastructure Freeze + Local AI Foundation
Goal: browser -> file upload -> backend -> local model -> response. Nothing agentic yet. (Combines original Day 0 + Day 1.)
# | Task Name | Description | Task Type | Priority | Status | Assigned To | Machine / Role | Dependencies | Notes / Differentiator Link
1 | Hardware & network freeze | Connect all 3 machines via one local offline switch (or hotspot with mobile data OFF). Verify MacBook can call both laptops' Ollama endpoints locally. | DevOps | Critical | Not Started | Vinit | (Orchestrator) | — | Do NOT change machines after this point.
2 | Install & freeze full software stack | Python/FastAPI/Uvicorn/Pydantic, Node/React/Tailwind/Framer Motion, PyMuPDF, python-docx, openpyxl, pandas, Tesseract/PaddleOCR, SQLite, FAISS/Qdrant. No installs during the event. | DevOps | Critical | Not Started | Meet | (Orchestrator) | —
3 | Ollama setup — Laptop 1 (Brain) | Install Ollama on Laptop 1, pull Llama-3.1-8B-Instruct 4-bit GGUF (~5.5GB). Confirm it answers a local prompt with internet off. | Backend/AI | Critical | Not Started | Piyush | Laptop 1 — Brain | —
4 | Ollama setup — Laptop 2 (Engine) + VRAM test | Install Ollama on Laptop 2, pull Qwen2.5-Coder-7B and Qwen2.5-VL-7B (both 4-bit). Test VL-7B on a REAL P&ID image, not just text — if it OOMs on 6GB, load a 2B-class VLM as fallback today, not later. | Backend/AI | Critical | Not Started | Vaibhav | Laptop 2 — Engine | — | Community guidance: VL-7B needs >6GB in practice — verify, don't assume.
5 | Build demo_data/ folder | inspection_report.pdf, scanned_report.pdf, sample_sop.pdf, maintenance_history.csv, equipment_image.png, sample_pid.png, previous_incident.pdf, report_template.docx, stale_sop_pair (Rev-2 vs Rev-4), prompt_injection_sample.pdf. | Assets | Critical | Not Started | Meet | (Orchestrator) | — | Feeds Differentiator #3 (stale-SOP) and P1 prompt-injection test.
6 | React frontend shell | Sidebar: Dashboard, Documents, AI Jobs, Knowledge, Artifacts, Audit, Network, Settings. Upload box, request box, Start Task button. | Frontend | Critical | Not Started | Ananya | Any client laptop | —
7 | FastAPI backend endpoints + job workspace | POST /upload, POST /task, GET /job/{id}, GET /artifact/{id}, GET /audit/{id}, GET /health. Job folder structure: /workspace/jobs/<job_id>/input, metadata.json, output/, audit.json. | Backend | Critical | Not Started | Vinit | MacBook (Orchestrator) | —
8 | Connect FastAPI to Laptop 1 (general model) | Wire backend to Ollama on Laptop 1. Test 'summarize this text' fully offline (internet cable pulled out). | Backend | Critical | Not Started | Piyush + Vinit | MacBook + Laptop 1 | Endpoints, Ollama Laptop 1
9 | Job state machine (skeleton) | RECEIVED -> PROCESSING -> RETRIEVING -> EXECUTING -> VERIFYING -> COMPLETED / FAILED. No agent logic yet, just state tracking. | Backend | High | Not Started | Meet | MacBook (Orchestrator) | Endpoints
10 | Frontend: wire upload -> Start Task -> raw response | Upload a PDF, hit Start Task, display the raw local-model response in the AI Jobs tab. | Frontend | High | Not Started | Aniket | Any client laptop | Frontend shell, backend endpoints
EXIT CRITERIA (must be true before moving to next day)
A PDF can be uploaded and receive a REAL response from the Laptop-1 local model with the internet cable physically pulled out. Do NOT touch today: GraphRAG, MCP, memory, multiple agents, 3D anything.

## Day 2
DAY 2 — Router + Bounded Agent
Goal: turn the chatbot into a task-aware, self-limiting agent with a visible, explainable decision trail.
# | Task Name | Description | Task Type | Priority | Status | Assigned To | Machine / Role | Dependencies | Notes / Differentiator Link
1 | Model registry (JSON) | {general: Llama-3.1-8B-Instruct-Q4, vision: Qwen2.5-VL-7B-Q4, coder: Qwen2.5-Coder-7B-Q4}. | Backend/AI | Critical | Not Started | Piyush | Laptop 1 — Brain | Day 1 model connections
2 | Rule-based router | PDF+summary -> general; image/P&ID -> vision; CSV+calculation -> coder; scanned PDF -> vision+OCR. Deterministic, not learned. | Backend/AI | Critical | Not Started | Piyush | Laptop 1 — Brain | Model registry
3 | Explainable Route Card logic (DIFFERENTIATOR #2) | For every task, capture: task type -> model selected -> WHY (capability match) -> models rejected -> confidence score. This is the object the frontend Route Card renders. | Backend/AI | Critical | Not Started | Piyush + Vaibhav | Laptop 1 + Laptop 2 | Router | Judges should be able to inspect the reasoning, not just see a label.
4 | Hot-swap logic, Laptop 2 (Coder <-> VL) | Swap Qwen2.5-Coder-7B and Qwen2.5-VL-7B on demand. Emit a visible 'Switching to vision model...' state to the backend — swap can take real seconds, don't hide it. | Backend/AI | High | Not Started | Vaibhav | Laptop 2 — Engine | Ollama Laptop 2
5 | Bounded agent state machine | INTAKE -> PLAN -> RETRIEVE -> ACT -> OBSERVE -> VERIFY -> COMPLETE. On VERIFY:FAIL -> REFLECT -> VERIFY. Guards: max_steps=8, max_retries=2. | Backend | Critical | Not Started | Meet | MacBook (Orchestrator) | Job state machine (Day 1)
6 | Operational trace (concise, no hidden chain-of-thought) | Emit only milestone events: 'Request understood -> Model selected -> Evidence retrieved -> Action executed -> Result verified -> Artifact generated.' | Backend | High | Not Started | Vinit | MacBook (Orchestrator) | Agent state machine
7 | Frontend: Route Card panel (DIFFERENTIATOR #2) | Show model chosen, the reason, rejected models, and confidence — live, per task, not buried in logs. | Frontend | Critical | Not Started | Ananya | Any client laptop | Route Card logic
8 | Frontend: Mission Card / agent trace | Reframe the agent trace as a numbered plan with a live completion count, e.g. '4/5 steps'. | Frontend | Medium | Not Started | Aniket | Any client laptop | Operational trace
9 | Test: routing + bounded stop | Confirm two different task types visibly select two different models, and the agent stops itself at the step/retry limit instead of looping forever. | QA | Critical | Not Started | Meet + Vinit | MacBook (Orchestrator) | All Day 2 tasks
EXIT CRITERIA (must be true before moving to next day)
Router visibly picks a different model for two different task types. Agent stops itself at the step/retry limit — no infinite loop. Route Card and Mission Card are both live in the UI, not console logs.

## Day 3
DAY 3 — RAG + Multimodal Understanding + Evidence Grounding
Goal: the system actually reads MRPL-style documents correctly and never presents an unsourced claim.
# | Task Name | Description | Task Type | Priority | Status | Assigned To | Machine / Role | Dependencies | Notes / Differentiator Link
1 | Digital PDF path | Text extraction -> chunking -> embedding -> vector DB (FAISS/Qdrant). | Backend | Critical | Not Started | Meet | MacBook (Orchestrator) | Day 1 stack
2 | Scanned PDF path (OCR + vision) | OCR (Tesseract/PaddleOCR) -> page image -> Qwen2.5-VL-7B on Laptop 2 for interpretation. | Backend/AI | Critical | Not Started | Vaibhav | Laptop 2 — Engine | Vision model hot-swap
3 | P&ID path | P&ID image -> vision model -> bounded question answering with a cited answer. | Backend/AI | Critical | Not Started | Vaibhav | Laptop 2 — Engine | Scanned PDF path
4 | Simple RAG (no GraphRAG) | query -> embedding -> top-5 chunks -> LLM -> answer WITH sources (document, page, revision, confidence). | Backend | Critical | Not Started | Piyush + Meet | Laptop 1 + MacBook | Digital PDF path, model registry
5 | CSV support (pandas) | Pandas-based filtering for structured queries, e.g. 'previous failures for Pump P101' against maintenance_history.csv. | Backend | High | Not Started | Vinit | MacBook (Orchestrator) | demo_data/
6 | Stale-SOP conflict detector (DIFFERENTIATOR #3) | Detect Rev-2 vs Rev-4 SOP pair. System must FLAG the conflict and stop instead of silently using the old document. | Backend | High | Not Started | Meet | MacBook (Orchestrator) | Simple RAG | This is the concrete proof-of-anti-hallucination, not a claim.
7 | Evidence object schema + API | Standard evidence object surfaced by every grounded answer: {document, page, revision, confidence}. | Backend | Critical | Not Started | Vinit | MacBook (Orchestrator) | Simple RAG
8 | Frontend: Evidence panel (DIFFERENTIATOR #3) | Every claim in an answer shows its source doc / page / revision / confidence, inline or on hover. | Frontend | Critical | Not Started | Ananya | Any client laptop | Evidence object schema
9 | Frontend: Knowledge tab | Browse locally indexed documents and chunks — proves the knowledge base is local, not a cloud call. | Frontend | Medium | Not Started | Aniket | Any client laptop | Digital PDF path
10 | HARD GATE — end-to-end grounded test | scanned_report.pdf -> OCR/vision -> evidence -> grounded answer with citation, fully working. If this fails, STOP adding features and fix this first before anything else. | QA | Critical | Not Started | Whole Team | All 3 machines | Everything above
EXIT CRITERIA (must be true before moving to next day)
THE LINE IN THE SAND: a scanned inspection report must produce a grounded, cited answer end-to-end by the end of today. If it doesn't, nothing built after this matters — fix it before adding anything new.

## Day 4
DAY 4 — Tools, Sandbox & the Real Deliverable
Goal: the agent does actual work and produces a real file that a human must sign off on.
# | Task Name | Description | Task Type | Priority | Status | Assigned To | Machine / Role | Dependencies | Notes / Differentiator Link
1 | Docker sandbox contract | network_mode: none, read-only input mounts, limited CPU/RAM/runtime, pre-baked pandas/scipy/python-docx. | DevOps | Critical | Not Started | Vinit | MacBook (Orchestrator) | Day 1 stack
2 | Tool: read_document | Reads source PDFs/text for the agent's ACT step. | Backend | High | Not Started | Meet | MacBook (Orchestrator) | Digital/scanned PDF paths
3 | Tool: search_knowledge | Queries the local vector DB for relevant evidence chunks. | Backend | High | Not Started | Meet | MacBook (Orchestrator) | RAG (Day 3)
4 | Tool: read_csv | Structured maintenance-history queries via pandas. | Backend | High | Not Started | Vinit | MacBook (Orchestrator) | CSV support (Day 3)
5 | Tool: run_python (sandboxed) | Executes engineering/data calculations inside the Docker sandbox, no network. | Backend | Critical | Not Started | Vinit | MacBook (Orchestrator) | Docker sandbox contract
6 | Tool: generate_docx | Sections: Purpose, Inspection Date, Key Findings, Evidence Table, Recommendations, Unresolved Items, Source References, Reviewer, plus an explicit 'AI-generated draft — human approval required' label. | Backend | Critical | Not Started | Meet | MacBook (Orchestrator) | Evidence object schema
7 | Tool: human_approval (DIFFERENTIATOR #5) | Backend logic that gates artifact finalisation on an explicit human action. The system must NEVER self-approve. | Backend | Critical | Not Started | Vinit | MacBook (Orchestrator) | generate_docx
8 | Frontend: Approve / Modify / Reject UI (DIFFERENTIATOR #5) | Three explicit buttons on every generated artifact — no auto-approve path anywhere in the UI. | Frontend | Critical | Not Started | Aniket | Any client laptop | human_approval tool
9 | Frontend: Artifacts tab + lineage | DOCX preview + download, plus 'this .docx came from these 3 files, these 2 models, this job ID' lineage line (reuses audit data). | Frontend | High | Not Started | Ananya | Any client laptop | generate_docx, audit log (Day 5 prelim)
10 | Exit test — scanned report to real artifact | scanned_report.pdf -> agent run -> real .docx that opens without error -> human approval action completed. | QA | Critical | Not Started | Whole Team | All 3 machines | Everything above
EXIT CRITERIA (must be true before moving to next day)
A scanned inspection report becomes a real, opens-without-error .docx file, and the human-approval gate works end-to-end — the system never self-approves.

## Day 5
DAY 5 — Sovereignty Proof, Security, Integration & SIH Demo
Goal: prove sovereignty live, then stabilise and rehearse. No new features once rehearsal starts. (Combines original Day 5 + Day 6.)
# | Task Name | Description | Task Type | Priority | Status | Assigned To | Machine / Role | Dependencies | Notes / Differentiator Link
1 | Default-deny firewall | Network isolation between the workbench and the internet; sandbox networking confirmed OFF. | Security | Critical | Not Started | Vinit | MacBook (Orchestrator) | Docker sandbox
2 | Live sovereignty monitor (DIFFERENTIATOR #1) | psutil-based socket/connection monitoring on the MacBook (NOT eBPF — macOS/Darwin doesn't support it natively). Shows local services ACTIVE, external calls 0, outbound traffic 0MB, sandbox network OFF. | Security | Critical | Not Started | Meet | MacBook (Orchestrator) | Firewall
3 | Audit log | Every action logged as {time, actor, event, tool, status}. | Security | Critical | Not Started | Meet | MacBook (Orchestrator) | Agent + tools (Day 2-4)
4 | SHA-256 hashing | Hash every input and output file; surface the hash in the UI next to the artifact. | Security | High | Not Started | Vinit | MacBook (Orchestrator) | Artifacts (Day 4)
5 | Live security demo script (DIFFERENTIATOR #1) | Attempt an internet call in front of the judge -> show it blocked, live, on screen -> continue the workflow locally. | Security | Critical | Not Started | Meet + Vinit | MacBook (Orchestrator) | Firewall, sovereignty monitor
6 | Frontend: Sovereignty / Network panel (DIFFERENTIATOR #1) | Local services / external calls / outbound traffic / sandbox network, live, always visible. | Frontend | Critical | Not Started | Ananya | Any client laptop | Sovereignty monitor
7 | Frontend: Audit tab | Event history + file hashes, human-readable. | Frontend | Medium | Not Started | Aniket | Any client laptop | Audit log
8 | Final 'wow' split-screen layout | Left: agent activity trace. Center: generated DOCX. Right: live sovereignty panel — AI + work + security + proof visible simultaneously. | Frontend | Critical | Not Started | Ananya + Aniket | Any client laptop | All panels built
9 | Full 3-machine integration pass | Run the flagship workflow end-to-end across all 3 machines; fix cross-machine bugs. | QA | Critical | Not Started | Piyush + Vaibhav + Meet + Vinit | All 3 machines | Day 1-4 complete
10 | Prepare the 4 judge-visible demos | 1) Auto model routing (route card live). 2) Scanned report -> approval note (full pipeline). 3) Coding in sandbox (pass/fail visible). 4) P&ID understanding (cited answer). | QA | Critical | Not Started | Whole Team | All 3 machines | Integration pass
11 | Two timed dry runs + 1 injected failure | Two full rehearsals timed end-to-end, plus one deliberately injected failure to show the retry/abstain path live. | QA | Critical | Not Started | Whole Team | All 3 machines | 4 demos ready
12 | Backup fallback output | Backup laptop/USB with a pre-generated fallback DOCX/output in case live inference stalls during the actual demo. | DevOps | High | Not Started | Vinit | USB / backup laptop | —
13 | Cable-unplug live test | Physically unplug the network cable mid-demo and confirm the UI reflects it live, without narration. | Security | Critical | Not Started | Meet | MacBook (Orchestrator) | Sovereignty panel
EXIT CRITERIA (must be true before moving to next day)
You can unplug the network cable mid-demo and the UI shows it live, without narration. All 4 judge demos work. Two full timed rehearsals completed, including one deliberate failure/retry demo, with a fallback output ready.

## Differentiation Checklist
KAVACH-AI — Differentiation Checklist (screenshot this)
Before you touch code, ask: is this plumbing (anyone can build it) or is this one of the 5 things below? If plumbing, keep it minimal and move on.
# | Differentiator | What the judge must SEE (not just hear) | Built On | Owner(s)
1 | Prove sovereignty, don't claim it | Live panel: local services ON, external calls = 0, outbound traffic = 0MB, sandbox network OFF. Then an internet call is attempted live and shown blocked. | Day 5 | Meet, Vinit, Ananya
2 | Explainable router, not a hidden if-else | Route Card: task type -> model chosen -> WHY -> models rejected -> confidence. Two different task types visibly pick two different models. | Day 2 | Piyush, Vaibhav, Ananya
3 | Evidence-first, every claim traceable | Every fact in the report links to document + page + revision. Stale-SOP pair (Rev-2 vs Rev-4) triggers a conflict flag, not a silent old answer. | Day 3 | Meet, Piyush, Ananya
4 | Bounded agent, controlled agency | Mission Card shows INTAKE->PLAN->RETRIEVE->ACT->OBSERVE->VERIFY live, with a step count. Agent self-stops at max_steps=8 / max_retries=2. | Day 2 | Meet, Aniket
5 | Real deliverable + human approval gate | An actual .docx opens cleanly, labelled 'AI-generated draft — human approval required', with Approve/Modify/Reject. System never self-approves. | Day 4 | Meet, Vinit, Aniket
THE ONE-LINE ANSWER FOR JUDGES
Problem: confidential industrial knowledge work (reports, SOPs, P&IDs) can't be sent to cloud AI, but employees still need an AI assistant that can read, reason over, and act on that data. Our answer: KAVACH-AI is not "Ollama + RAG + DOCX" (a weekend build). It is an agentic workbench that (1) proves — live, on screen — that zero data leaves the building, (2) explains every model routing decision instead of hiding it, (3) grounds every claim to a page and revision and refuses to use stale evidence silently, (4) bounds its own agency so it can never loop forever, and (5) never signs its own work — a human always approves the final artifact.
WHAT TO SAY IF A JUDGE ASKS "ANYONE CAN CONNECT 4 SYSTEMS ON A LAN"
True — the LAN is infrastructure, not the product. The product is everything running ON TOP of it: the explainable router, the evidence/revision grounding, the bounded agent, the human-approval gate, and — most importantly — the LIVE, VISIBLE proof of sovereignty (the blocked network call). Connecting machines is the foundation; proving trust and control on top of that foundation is what we built.

## Demo Data & Scope
demo_data/ Checklist + P0 / P1 / P2 Scope Control
demo_data/ — must exist and be validated by end of Day 1
# | File | Purpose | Prepared By | Status
1 | inspection_report.pdf | Primary engineering inspection input (digital PDF path) | Meet / Vinit | Not Started
2 | scanned_report.pdf | OCR + vision path — the Day-3 hard-gate test file | Meet / Vinit | Not Started
3 | sample_sop.pdf | Grounding source for evidence-first answers | Meet / Vinit | Not Started
4 | maintenance_history.csv | Structured maintenance evidence for the CSV tool | Meet / Vinit | Not Started
5 | equipment_image.png | Vision model input | Meet / Vinit | Not Started
6 | sample_pid.png | P&ID understanding demo | Meet / Vinit | Not Started
7 | previous_incident.pdf | Historical context document | Meet / Vinit | Not Started
8 | report_template.docx | Formatting template for generate_docx | Meet / Vinit | Not Started
9 | stale_sop_pair.pdf (Rev-2 vs Rev-4) | Feeds Differentiator #3 — conflict detection demo | Meet / Vinit | Not Started
10 | prompt_injection_sample.pdf | P1 robustness test — retrieved text must never override system rules | Meet / Vinit | Not Started
P0 — must have for the demo to work at all
✔ | Web UI
✔ | Local LLM (general)
✔ | Rule-based router + Route Card
✔ | Bounded agent
✔ | RAG (digital + scanned)
✔ | OCR
✔ | Vision / P&ID
✔ | DOCX generation
✔ | Verification
✔ | Human approval gate
✔ | Network / sovereignty proof
✔ | Audit log + hashing
P1 — only if P0 is done early (cheap, reuses P0 data)
~ | Knowledge conflict detector (stale SOP)
~ | Failure -> recovery demo (retry/abstain)
~ | Prompt-injection defense
~ | Local data lineage on artifacts
~ | AI Red Team Score (aggregate pass/fail)
~ | Uncertainty budget (known/inferred/unknown counts)
P2 — cut without guilt (do not attempt in 5 days)
✘ | AI Watchtower
✘ | Evidence map graph visualization
✘ | GraphRAG
✘ | Temporal knowledge graph
✘ | Learned router
✘ | 3D refinery
✘ | Sensor simulation
✘ | MemGPT / long-term memory
✘ | Multi-agent (AutoGen-style) orchestration